## Sheet1
ONLINE BANKING
S.No | Date | ActionPlanned
1 | Fri: 08-11-2019 | Analysis of Project
2 | Sat: 09-11-2019 | Discussion on UI, DataBase Modules
3 | Mon: 11-11-2019 | Design of DataBase
4 | Mon: 11-11-2019 | Designing the UI Module(HomePage before Login)
5 | Tue:12-11-2019 | SubPages (HomePage before Login) & Designing the UI Module(HomePage after Login)
6 | Wed: 13-11-2019 | Validation and logic of login
7 | Thurs: 14-11-2019 | Admin and open_saving_account_page logic
8 | Fri: 15-11-2019 | Sprint 1: Submission of UI, DataBase & Logics
9 | Sat: 16-11-2019 | Sending Account_no Via Email to user
10 | Mon: 18-11-2019 | Assessment
11 | Tue: 19-11-2019 | Sending Account_no Via Email to user
12 | Wed: 20-11-2019 | Module-1 OTP and Emai(Register)l,{Module2(Dashboard-UserDetails) and Module3(AddPayee-Benificiary)}
13 | Thurs: 21-11-2019 | Module -3 Transaction different modes,{Module2(Dashboard-Account_satement)}
14 | Fri: 22-11-2019 | Module -3{transaction different modes},Change Password,Forgotten Password
15 | Sat: 23-11-2019 | Module -3{transaction different modes}, AddPayee(issue resolve),Module-1 OTP and Email (register)(issue)
16 | Mon: 24-11-2019 | Sample Testing
17 | Tue: 25-11-2019 | Validations,ErrorHandling
18 | Wed: 26-11-2019 | Exceptional Handling and Encryption , Decryption