## Women Empowerment Team1
Role
Month And Date |  | Tirumala V Kulkarni | Rashmi R V | Neha Vijayananda | Vineet Mallya
Nov | 19 | Analyzing the case study | Analyzing the case study | Analyzing the case study | Analyzing the case study
Nov | 20 | DB Design | DB Design | DB Design | DB Design
Nov | 21 | Inserting Values into Passenger module | Inserting Values into Admin module | Layout design | Layout Design
Nov | 22 | Stored Procedure for show tickets | stored procedure for search flight | Admin ,User Login page | Contact,About,Home Page
Nov | 23 |  |  | Book tickets page,Detailed Search Page | Admin pages design
Nov | 24 | Passenger and Seat Logic | Admin controllers and Search controller | Ticket Display Page | Search Page,Javascript for seat booking and UI
Nov | 25 | Integration | Test module and exception handling | Enchancing of UI | Enhancing of UI
Nov | 26 | Testing project | Testing project | Testing project | Testing project
Nov | 27

## Checklist
S.No | Parameters | Team 1
1 | Comments
2 | Region
3 | Variable handled--> Scope
4 | Decorators (isNull)
5 | for/foreach(standard)
6 | Array/Collecton/enum,struct
7 | Function, overloading,overriding
8 | Abstract/sealed
9 | Interface
10 | Try/catch
11 | Layout- header/footer
12 | External site- target=_blank
13 | Sql - use index
14 | Search
15 | Dropdown binding - dynamic
16 | Ajax
17 | Responsive website
18 | Partial views
19 | No hard coding
20
Note on C21: Shiny